## Scorecard
Governance and Cost Review Scorecard - Pashun Sports multi-agent system
Score each criterion from 0 to 5 (0 = nothing in place, 3 = partly in place, 5 = fully in place and tested). Weights must total 100. Yellow cells are inputs; scores shown are a worked example.
Area | Criterion | Weight | Score (0-5) | Weighted score | Status | Owner | Evidence / next action
Architecture | Each agent has one clear job and a routing description with a boundary statement | 12 | 4 |  |  | Paul Ashun | Four agents have descriptions; the ambiguous "order is late" probe fixed by tightening descriptions
Architecture | Front door holds no deep domain knowledge (routing plus fallback only) | 5 | 5 |  |  | Paul Ashun | Front door stripped back to routing plus fallback
Knowledge | Each specialist has only the knowledge it needs; sources are approved | 8 | 4 |  |  | Jamie Jordan | Customer Policies, Ridgeline agreement and sales workbook only
Security | DLP policy with Business / Non-Business / Blocked applied to Production | 10 | 4 |  |  | Paul Ashun | DLP applied; confirm Production scope
Security | Sharing restricted to an Entra security group (PS-All-Employees); Authenticate with Microsoft | 10 | 5 |  |  | Paul Ashun | PS-All-Employees group set; Authenticate with Microsoft on all four
Security | Wholesale prices and other restricted data cannot be reached (tested) | 8 | 5 |  |  | Morgan Reyes | Wholesale price probe refused and logged
Lifecycle | Solution-based promotion Dev > Test > Production; tests rerun in Test | 14 | 4 |  |  | Jamie Jordan | Solution exported Dev to Test; Production import pending
Cost | Forecast built in the Agent Usage Estimator with 30% contingency and a worst case | 10 | 4 |  |  | Morgan Reyes | Estimator done; worst case still to add
Cost | Forecast compared with the Capacity page; billing alert at 80% | 9 | 3 |  |  | Morgan Reyes | Capacity page checked once; alert not set yet
Operations | Monthly review scheduled with an owner per agent | 9 | 3 |  |  | Jamie Jordan | First review booked, owners to confirm
Operations | Monitor metrics tracked: engagement, resolution, escalation, abandoned sessions | 5 | 3 |  |  | Jamie Jordan | Monitor tab opened; no baseline yet
Totals
Weights total check
Overall score (%)
Rating
Red items
Amber items
Weighted score by area (see Area Summary sheet)

## Area Summary
Area | Weight | Weighted score | Area score (%) | Status
Architecture
Knowledge
Security
Lifecycle
Cost
Operations

## Monthly Agent Review
Agent | Owner | Engagement rate | Resolution rate | Escalation rate | Abandoned sessions rate | Target escalation rate (max) | Target resolution rate (min) | Escalation check | Resolution check | Top 3 improvements | Credits used this month | Credits forecast | Credit variance
PS-Project-Support-Helper | Jamie Jordan |  |  |  |  | 12% | 70%
PS-Customer-Service | Jamie Jordan |  |  |  |  | 12% | 70%
PS-Supplier-Follow-Up | Jamie Jordan |  |  |  |  | 12% | 70%
PS-Sales-Reporter | Morgan Reyes |  |  |  |  | 12% | 70%
Enter last month's figures from the Monitor tab (engagement, resolution, escalation, abandoned sessions) and credit use from the Capacity page. Targets are starting points: agree your own with each owner. Targets of 12% escalation and 70% resolution are examples only.

## Top 3 Governance Gaps
Gap | Area (DLP / ownership / sharing scope / other) | Why it matters | Owner (named person) | Fix by | Status
Example: Production DLP policy not yet reviewed after Operations Agent added | DLP | A new connector could mix Business and Non-Business groups | Paul Ashun | Nov 30, 2026 | Open